|  |
| --- |
| ***2022******KPQC Fourth Trimester Initiative******Champion Timeline*** |
| ***FIT Project*** | ***Start*** | ***Finish*** | ***May*** | ***June*** | ***July*** | ***Aug*** | ***Sept*** | ***Oct*** | ***Nov*** | ***Dec*** |
| **POSTBIRTH Training** | Current | June 2022 (up to Sept 2022) |  |  | Up to September 2022 |  |  |  |
| **KBEN Training** | May 24, 2022 | Sept 30, 2022 (check in June 2022, July 2022) |  | June“Check in” | July“Check in” |  |  |  |  |  |
| **MMH TA** | Current | Ongoing thru 2022 |  |  |  |  |  |  |  |  |
| **PP Policy Update** | Current | Ongoing thru 2022 |  |  |  |  |  |  |  |  |
| **PP Appointment** | Current | December 2022 |  |  |  |  |  |  |  |  |
| **Data Entry** | June 2022 | Ongoing thru 2022 |  |  |  |  |  |  |  |  |
| **PP Care Team/PP Referrals/Community Resource List** | July 2022 | December 2022 |  |  |  |  |  |  |  |  |
| **Breastfeeding** | June 2022 | Ongoing thru 2022 |  |  |  |  |  |  |  |  |
| **SSDOH Screening & Referral to CRL** | TBD |  | **TBD** |
| **Standardized Discharge Summary** | TBD |  | **TBD** |
| **Reproductive Life Planning** | TBD |  | **TBD** |
| **Patient Voice** | TBD |  | **TBD** |